## Daily Work Log
Date | Member Name | Module | Hours Worked | Status | Work Description (What did you do today?)
2026-07-06 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Finalized RAG architecture with Guide Er. Ram Babu Buri; drafted project abstract and registration.
2026-07-06 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Researched Kaggle academic paper datasets (arXiv CS AI/ML corpus) for document extraction.
2026-07-06 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Researched PostgreSQL pgvector extension and Neon serverless database deployment.
2026-07-06 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Researched Electron 30 with React 18 and TypeScript for cross-platform desktop delivery.
2026-07-06 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Researched RAG Triad evaluation metrics (Context Relevance, Faithfulness, Answer Relevance).
2026-07-07 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Convened kickoff meeting; defined 5-module boundaries and GitHub workflow for team.
2026-07-07 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Evaluated Apache Tika and PDFBox libraries for handling complex Kaggle research paper PDFs.
2026-07-07 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Provisioned Neon PostgreSQL development instance and verified remote JDBC connectivity.
2026-07-07 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Evaluated Tailwind CSS and Lucide icons for dark-mode responsive UI design.
2026-07-07 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Evaluated JUnit 5, Mockito, and Testcontainers setup for Spring Boot automated testing.
2026-07-08 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Established repository branching policy (minimum 3 commits/student/week) on GitHub.
2026-07-08 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Defined Document Ingestion module boundary and input MIME format validation standards.
2026-07-08 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Evaluated Spring Boot pgvector drivers and HNSW vector index compatibility.
2026-07-08 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Drafted wireframe layouts for Chat Canvas, Citation Inspector, and Ingestion Panel.
2026-07-08 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Drafted QA test coverage targets (>80%) and golden dataset validation plan.
2026-07-09 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Drafted high-level RAG orchestration flow and context assembly specifications.
2026-07-09 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Analyzed mathematical equations and two-column layout parsing challenges in academic papers.
2026-07-09 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Drafted relational schemas for user authentication, roles, document metadata, and chunks.
2026-07-09 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Researched Electron IPC security best practices (contextIsolation, sandboxed preload).
2026-07-09 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Formulated mathematical evaluation formulas for measuring hallucination rates.
2026-07-10 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Attended Saturday mentor review; defended architectural scope with Er. Ram Babu Buri.
2026-07-10 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Participated in Saturday mentor review; confirmed Kaggle dataset curation parameters.
2026-07-10 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Attended Saturday mentor review; presented database connection pooling architecture.
2026-07-10 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated UI wireframe concepts to mentor Er. Ram Babu Buri during Saturday review.
2026-07-10 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Participated in Saturday mentor review; discussed evaluation criteria with mentor.
2026-07-11 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Compiled mentor notes and aligned week 2 SRS deliverables with team.
2026-07-11 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Documented text normalization rules and prepared next week's parser requirements.
2026-07-11 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Documented database performance objectives and connection limits in Neon.
2026-07-11 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Documented desktop client packaging and performance requirements.
2026-07-11 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Established testing directory structure and test metrics documentation repository.
2026-07-13 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Authored SRS Functional Requirements for Core RAG Service (query embedding, prompt assembly, SSE stream).
2026-07-13 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Authored SRS Functional Requirements for Ingestion (Kaggle dataset multi-file upload, Tika extraction).
2026-07-13 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Authored SRS Data Requirements: PostgreSQL 16 schema, pgvector vector(1536) columns.
2026-07-13 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Authored SRS User Interface Requirements: Electron desktop shell, React responsive layout.
2026-07-13 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Authored SRS Testing Requirements: unit test coverage (>80%), end-to-end integration tests.
2026-07-14 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Specified non-functional performance requirements: retrieval latency <120ms, error fallback.
2026-07-14 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Specified chunking requirements: recursive splitting, 500-token window, 50-token overlap.
2026-07-14 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Defined Security Requirements: JWT HMAC-SHA256 tokens, BCrypt password hashing, RBAC.
2026-07-14 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Specified real-time chat streaming UI, code block syntax highlighting, and markdown rendering.
2026-07-14 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Specified RAG Triad evaluation metrics requirements: Context Recall, Precision, Faithfulness.
2026-07-15 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Authored SRS Section 2: Overall System Description and Operating Environment.
2026-07-15 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Defined error handling requirements for corrupted files, scanned PDFs, and oversized uploads.
2026-07-15 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Documented HNSW index parameters (m=16, ef_construction=64) on Neon serverless.
2026-07-15 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Defined desktop client offline behavior, local cached credentials, and network indicators.
2026-07-15 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Defined compliance checklist for IEEE 830 standards across all 5 modules.
2026-07-16 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Specified REST API contract for /api/rag/chat and Server-Sent Events streaming.
2026-07-16 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Specified asynchronous job tracking status lifecycle (UPLOADED -> PARSING -> INDEXED).
2026-07-16 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Specified audit logging requirements for user queries, tokens used, and upload timestamps.
2026-07-16 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Drafted UI navigation hierarchy and screen transition specifications.
2026-07-16 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Compiled individual module SRS sections into unified 35-page master SRS document.
2026-07-17 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Attended Saturday mentor review; reviewed RAG functional specifications with mentor.
2026-07-17 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Attended Saturday mentor review; defended parsing throughput and file size constraints (25MB).
2026-07-17 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented database and security section to mentor during Saturday review.
2026-07-17 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Reviewed UI SRS requirements with mentor; received approval on split-pane workspace layout.
2026-07-17 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented quality assurance and evaluation criteria during Saturday review.
2026-07-18 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Incorporated mentor suggestions on similarity confidence threshold filtering.
2026-07-18 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Updated document ingestion requirements matrix in master SRS document.
2026-07-18 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Finalized Neon database capacity planning and SSL/TLS constraints in SRS.
2026-07-18 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Refined desktop application performance requirements (RAM consumption <150MB).
2026-07-18 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Created SRS traceability matrix mapping requirements to development milestones.
2026-07-20 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Drafted system-level Use Case Diagram mapping Actors (Student, Researcher, Admin) to actions.
2026-07-20 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Designed Sequence Diagram for Kaggle Ingestion: Upload -> MIME Validator -> Parser -> Chunker.
2026-07-20 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Designed Entity-Relationship (ER) Diagram: Users, Roles, Documents, DocumentChunks, AuditLogs.
2026-07-20 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Designed Component Diagram showing Electron Main, Preload Bridge, React Renderer, and SSE Client.
2026-07-20 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Designed Sequence Diagram for Automated RAG Evaluation Pipeline (Test Runner -> Triad Evaluator).
2026-07-21 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Designed Sequence Diagram for RAG Query Processing: User -> Electron -> Spring Boot -> Neon -> LLM.
2026-07-21 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Constructed Class Diagram for DocumentParser, TikaParserImpl, and RecursiveTextChunker.
2026-07-21 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Constructed Class Diagram for JPA entities: User, Role, Document, DocumentChunk.
2026-07-21 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Constructed Sequence Diagram for desktop file drag-and-drop ingestion to Spring Boot API.
2026-07-21 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Constructed Component Diagram for Test Automation and Telemetry collector in Spring Boot.
2026-07-22 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Constructed Class Diagram for RagOrchestrationService, PromptTemplateBuilder, and ChatClient.
2026-07-22 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Modeled State Machine Diagram for DocumentStatus (UPLOADED -> PARSING -> CHUNKED -> INDEXED).
2026-07-22 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Designed Sequence Diagram for User Authentication and JWT verification filter chain.
2026-07-22 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Modeled UI State Flow Diagram: Auth Guard -> Workspace Selection -> Chat Session -> Citations.
2026-07-22 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Created UML Traceability Matrix cross-referencing SRS functional requirements to UML classes.
2026-07-23 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Modeled State Machine Diagram for conversational session lifecycle and context budgeting.
2026-07-23 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Designed Activity Diagram illustrating token-aware recursive text splitting with sliding window.
2026-07-23 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Modeled database physical deployment schema with Neon connection pooler and pgvector extension.
2026-07-23 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Designed Class/Interface Diagram for React State Stores (useChatStore, useDocStore).
2026-07-23 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Drafted Deployment Diagram showing Client Electron App, Cloud Spring Boot Service, and Neon DB.
2026-07-24 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Presented RAG UML sequence and class diagrams to mentor Er. Ram Babu Buri during Saturday review.
2026-07-24 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Reviewed Ingestion UML models with mentor; clarified multipart file streaming boundary.
2026-07-24 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented ER diagram and security sequence diagrams to mentor during Saturday review.
2026-07-24 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Reviewed Electron architectural component diagram with mentor; confirmed IPC security boundaries.
2026-07-24 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented overall deployment architecture and evaluation UML models in Saturday mentor review.
2026-07-25 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Refined Class Diagram methods based on mentor recommendations for loose coupling.
2026-07-25 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Finalized document ingestion package diagram in UML specification document.
2026-07-25 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Adjusted foreign key cascading rules (ON DELETE CASCADE) per mentor input.
2026-07-25 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Compiled UI design artifacts and component interaction specs into UML design report.
2026-07-25 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Assembled all UML diagrams into Chapter 3 of Project Design Documentation.
2026-07-27 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Set up local IDE with Spring Boot 3.3, Java 21, and Spring AI milestone dependencies.
2026-07-27 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Configured Maven dependencies for Apache Tika Core/Parsers and Apache PDFBox 3.x.
2026-07-27 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Created Neon PostgreSQL database instance; executed 'CREATE EXTENSION IF NOT EXISTS vector;'.
2026-07-27 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Initialized React 18 + TypeScript frontend using Vite; configured Tailwind CSS and Lucide icons.
2026-07-27 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Configured JUnit 5, AssertJ, and Mockito testing dependencies in Maven POM.
2026-07-28 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Created root Maven multi-module parent POM structure with defined member sub-modules.
2026-07-28 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Downloaded sample research paper dataset from Kaggle (arXiv multi-domain corpus).
2026-07-28 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Authored DDL migration script: created tables users, roles, documents, document_chunks.
2026-07-28 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Set up Electron 30.x desktop scaffolding with secure contextIsolation and preload script.
2026-07-28 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Set up H2 in-memory test profile with pgvector mock functions for unit test runs.
2026-07-29 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Drafted Spring AI VectorStore interface abstraction and mock embedding generator.
2026-07-29 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Created Git branch 'feature/member2-doc-ingestion' and committed base document model interfaces.
2026-07-29 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Created HNSW index on document_chunks(embedding vector_cosine_ops) for sub-100ms similarity search.
2026-07-29 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Created Git branch 'feature/member4-ui-electron' and pushed base desktop client skeleton.
2026-07-29 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Created Git branch 'feature/member5-analytics-evaluation' and initialized test harness structure.
2026-07-30 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Configured application-dev.yml and environment variable templates for API keys and DB credentials.
2026-07-30 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Tested text boundary detection and cleaning of whitespace, headers, and footers on Kaggle papers.
2026-07-30 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Created Git branch 'feature/member3-database-security' and committed Flyway migration scripts.
2026-07-30 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Built responsive UI layout: Collapsible Sidebar, Main Chat Canvas, Source Citation Drawer.
2026-07-30 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Drafted automated test suites for verifying database schema integrity and constraints.
2026-07-31 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Attended Saturday mentor review; verified development toolchain and Maven build with mentor.
2026-07-31 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Participated in mentor review; demonstrated prototype parsing results for complex Kaggle PDFs.
2026-07-31 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented live Neon DB connection and vector table schema to mentor during review.
2026-07-31 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated running Electron desktop shell to mentor during Saturday review.
2026-07-31 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Reviewed testing plan and Git branch workflow with mentor Er. Ram Babu Buri.
2026-08-01 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Created initial Git branch 'feature/member1-rag-engine' and pushed initial RAG service boilerplate.
2026-08-01 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Documented token count estimation utility using JTokkit (BPE tokenizer for Java).
2026-08-01 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Verified Neon SSL/TLS connection parameters and HikariCP connection pool settings in Spring Boot.
2026-08-01 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Tested Hot Module Replacement (HMR) inside Electron development environment.
2026-08-01 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Created GitHub Actions CI workflow draft for automated build verification on pull requests.
2026-08-03 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Implemented RagOrchestrationServiceImpl: handles incoming query, generates query vector, queries vector store.
2026-08-03 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Implemented TikaDocumentParser: extracts clean text and metadata (author, title, page count) from Kaggle PDFs.
2026-08-03 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Implemented Spring Security 6 security filter chain with stateless SessionCreationPolicy.STATELESS.
2026-08-03 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Implemented ChatMessage component in React supporting User, Assistant, and System message bubbles.
2026-08-03 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Implemented Unit test suite for RecursiveTextChunker (tested overlap accuracy, boundary conditions).
2026-08-04 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Created PromptTemplateBuilder with customizable system instructions, contextual citation constraints, and tone.
2026-08-04 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Implemented RecursiveTextChunker: splits text into configurable chunk sizes (500 tokens) with 50-token overlap.
2026-08-04 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Created JwtTokenProvider: generates and validates HMAC-SHA256 JWT tokens with role claims.
2026-08-04 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Added Markdown rendering using react-markdown with remark-gfm (tables, lists, inline code).
2026-08-04 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Implemented Unit tests for JwtTokenProvider (valid token parsing, expired token rejection, signature forgery).
2026-08-05 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Implemented context truncation logic to ensure retrieved passages fit within LLM context window limits.
2026-08-05 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Added sentence boundary preservation using Java BreakIterator to avoid mid-sentence splits.
2026-08-05 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Implemented JwtAuthenticationFilter: intercepts requests, extracts Bearer token, sets SecurityContext.
2026-08-05 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Implemented Prism.js code syntax highlighting with copy-to-clipboard button in assistant responses.
2026-08-05 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Created mock data generators for sample academic papers, user profiles, and test embeddings.
2026-08-06 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Added custom exception classes: RagException, ContextNotFoundException, EmbeddingServiceUnavailableException.
2026-08-06 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Created DocumentMetadata entity and assigned unique UUID chunk identifiers linked to parent document.
2026-08-06 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Created AuthController with /api/auth/register and /api/auth/login endpoints with BCrypt password encoding.
2026-08-06 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Created ChatInput component with multi-line auto-resizing textarea and submit on Enter.
2026-08-06 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Added Jacoco code coverage plugin to Maven build and generated initial coverage reports.
2026-08-07 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Attended Saturday mentor review; demonstrated prompt assembly and retrieval query pipeline in console.
2026-08-07 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Demonstrated multi-page document parsing and chunking output during Saturday mentor review.
2026-08-07 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented user registration and JWT authentication flow to mentor during review.
2026-08-07 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated React chat interface running in Electron window during mentor review.
2026-08-07 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Reviewed test execution results and coverage metrics with mentor during Saturday review.
2026-08-08 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed module updates to branch 'feature/member1-rag-engine' (3 commits verified this week).
2026-08-08 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed parser and chunker implementation to branch 'feature/member2-doc-ingestion' (3 commits).
2026-08-08 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed security filter chain and auth controllers to 'feature/member3-database-security' (3 commits).
2026-08-08 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed UI components and layout state to branch 'feature/member4-ui-electron' (3 commits).
2026-08-08 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed test suites to branch 'feature/member5-analytics-evaluation' (3 commits).
2026-08-10 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Integrated Spring AI EmbeddingModel client (configured for text-embedding-3-small / local embeddings).
2026-08-10 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Implemented DocumentUploadController with POST /api/documents/upload handling multipart file uploads.
2026-08-10 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Implemented PgVectorChunkRepository using Spring Data JPA and native SQL for vector similarity search.
2026-08-10 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Implemented FileUploadZone component with drag-and-drop support and file type validation badges.
2026-08-10 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Implemented integration tests for DocumentUploadController using Spring MockMvc.
2026-08-11 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Implemented EmbeddingCacheService using Spring Cache (Caffeine) to prevent re-embedding identical user queries.
2026-08-11 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Added MIME type validation and file size check (rejects files >25MB with HTTP 413 Payload Too Large).
2026-08-11 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Created native query: 'SELECT *, 1 - (embedding <=> :queryVector) AS similarity FROM document_chunks ORDER BY embedding <=> :queryVector LIMIT :topK'.
2026-08-11 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Built DocumentManagerDrawer displaying list of indexed documents, page counts, chunk stats, and delete action.
2026-08-11 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Tested file validation constraints (rejected malicious extensions, oversized files, empty files).
2026-08-12 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Created HybridRetriever: combines vector cosine similarity with BM25 keyword matching for improved recall.
2026-08-12 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Implemented async ingestion worker (@Async Spring TaskExecutor) to prevent blocking HTTP request thread.
2026-08-12 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Added metadata filtering support (filter by documentId, uploadDate, and user ownership).
2026-08-12 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Integrated Axios client with JWT interceptor: automatically attaches 'Authorization: Bearer <token>' to requests.
2026-08-12 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Created benchmark script testing vector insertion throughput for 100-page document (recorded ~3.2s total time).
2026-08-13 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Added fallback response generator when vector similarity score is below confidence threshold (0.65).
2026-08-13 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Added DocumentStatus update callbacks (PROCESSING -> CHUNKING -> EMBEDDING -> INDEXED).
2026-08-13 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Configured HikariCP connection pool settings optimized for Neon serverless idle timeout handling.
2026-08-13 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Added upload progress bar showing real-time upload percentage and processing spinner.
2026-08-13 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Added memory profiling checks using VisualVM during document chunking and embedding operations.
2026-08-14 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Participated in Saturday mentor review; demonstrated embedding generation and cache hits.
2026-08-14 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Demonstrated asynchronous file upload and processing status polling in mentor review.
2026-08-14 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented pgvector similarity search performance query plan to mentor during review.
2026-08-14 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated file upload and document management UI inside Electron to mentor.
2026-08-14 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Reported benchmark metrics to mentor; verified memory footprint remained stable under 512MB heap.
2026-08-15 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed hybrid retrieval and caching enhancements to branch 'feature/member1-rag-engine' (3 commits).
2026-08-15 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed upload controller and async pipeline to 'feature/member2-doc-ingestion' (3 commits).
2026-08-15 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed vector repository and native query methods to 'feature/member3-database-security' (3 commits).
2026-08-15 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed document management UI components to branch 'feature/member4-ui-electron' (3 commits).
2026-08-15 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed integration test cases to branch 'feature/member5-analytics-evaluation' (3 commits).
2026-08-17 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Implemented StreamingChatController using Spring WebFlux SseEmitter for token-by-token streaming.
2026-08-17 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Implemented DocumentSummaryService: generates automatic 3-sentence executive summary upon document indexing.
2026-08-17 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Implemented Role-Based Access Control (RBAC): created roles ROLE_ADMIN, ROLE_RESEARCHER, ROLE_STUDENT.
2026-08-17 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Implemented EventSource / fetch stream consumer in React for real-time SSE token rendering.
2026-08-17 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Implemented automated integration tests for SSE streaming endpoint using WebTestClient.
2026-08-18 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Built SourceCitationInjector: appends verified chunk IDs and document metadata to the final SSE event.
2026-08-18 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Added document deletion and cascade purge: cleans up document metadata, raw file, and vector chunks in Neon.
2026-08-18 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Secured sensitive endpoints: restricted document deletion and admin metrics to ROLE_ADMIN.
2026-08-18 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Built SourceCitationBadge component: clicking a citation badge opens the exact source excerpt modal.
2026-08-18 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Created test scenario verifying rate-limiting enforcement (tested 31st request receives HTTP 429).
2026-08-19 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Implemented ConversationHistoryManager: maintains rolling multi-turn memory window per session.
2026-08-19 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Implemented chunk preview endpoint: GET /api/documents/{id}/chunks returning chunk text and token sizes.
2026-08-19 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Implemented RateLimitingFilter using Bucket4j (token bucket algorithm: max 30 requests/minute per IP).
2026-08-19 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Integrated Electron native notifications when background document indexing completes.
2026-08-19 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Tested RBAC enforcement: verified non-admin users cannot access administrative document delete endpoints.
2026-08-20 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Added token-usage tracking per query session (prompt tokens, completion tokens, latency ms).
2026-08-20 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Added support for plain text (.txt) and Markdown (.md) ingestion alongside PDF files.
2026-08-20 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Added AuditLogEntity and AuditService: logs query timestamp, user ID, tokens consumed, and execution status.
2026-08-20 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Added chat session persistence in LocalStorage with export chat to Markdown/PDF option.
2026-08-20 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Set up JaCoCo report pipeline tracking unit test coverage across all newly merged features.
2026-08-21 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Demonstrated real-time token streaming to mentor Er. Ram Babu Buri during Saturday review.
2026-08-21 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Presented document summary and preview feature during Saturday mentor review.
2026-08-21 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented security access control and rate limiter verification to mentor during review.
2026-08-21 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated interactive citations and token typing animation to mentor during Saturday review.
2026-08-21 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented security and rate-limiting test audit to mentor during Saturday meeting.
2026-08-22 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed streaming controller and citation builder to 'feature/member1-rag-engine' (3 commits).
2026-08-22 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed summary service and document lifecycle endpoints to 'feature/member2-doc-ingestion' (3 commits).
2026-08-22 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed security annotations and audit service to 'feature/member3-database-security' (3 commits).
2026-08-22 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed streaming UI hook and citation modal to 'feature/member4-ui-electron' (3 commits).
2026-08-22 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed security test suites to 'feature/member5-analytics-evaluation' (3 commits).
2026-08-24 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Added Temperature and Top-P runtime tuning parameters to ChatRequest DTO for experimental variability.
2026-08-24 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Optimized Apache Tika memory usage during large document parsing by streaming parser buffers.
2026-08-24 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Created AdminAnalyticsRepository with custom JPA aggregation queries for query volume and average latency.
2026-08-24 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Built AdminDashboard component with Recharts: Query Volume over time, Latency histogram, Token cost chart.
2026-08-24 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Implemented RagEvaluationService: computes Context Precision, Groundedness/Faithfulness, and Answer Relevance.
2026-08-25 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Implemented re-ranking module prototype: scores top-10 retrieved chunks and selects top-4 for prompt context.
2026-08-25 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Implemented batch document re-indexing endpoint for administrative knowledge base maintenance.
2026-08-25 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Implemented GET /api/admin/metrics returning total queries, active users, vector chunks count, and storage used.
2026-08-25 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Implemented SystemSettings panel allowing configuration of Backend API URL, LLM model choice, and dark/light theme.
2026-08-25 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Created automated evaluation test runner with a golden dataset of 50 ground-truth Q&A pairs from Kaggle.
2026-08-26 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Refactored PromptTemplateBuilder to inject explicit negative constraints ('Answer only from context, else state unknown').
2026-08-26 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Added support for extracting and indexing image captions and metadata from PDF files.
2026-08-26 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Created database backup and restore script for Neon PostgreSQL vector tables using pg_dump/pg_restore.
2026-08-26 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Created desktop application title bar with native minimize, maximize, and close controls in Electron.
2026-08-26 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Recorded baseline scores: Context Relevance = 0.88, Faithfulness = 0.92, Answer Relevance = 0.90.
2026-08-27 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Added structured JSON output mode for programmatic Q&A extraction.
2026-08-27 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Curated Kaggle dataset benchmark of 25 technical research papers and textbook chapters for system benchmark.
2026-08-27 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Optimized SQL query performance by adding composite index on document_chunks(document_id, chunk_index).
2026-08-27 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Polished responsive UI typography, scrollbars, and tooltips across the desktop application.
2026-08-27 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Built REST endpoint GET /api/admin/evaluation returning historical evaluation scores and hallucination rates.
2026-08-28 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Reviewed re-ranking quality improvements with mentor during Saturday review.
2026-08-28 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Demonstrated batch re-indexing and document benchmark corpus to mentor.
2026-08-28 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Demonstrated database analytics queries and Neon storage telemetry to mentor.
2026-08-28 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated full Admin Dashboard and desktop customizations to mentor during Saturday review.
2026-08-28 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented evaluation methodology and live benchmark score report to mentor Er. Ram Babu Buri.
2026-08-29 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed re-ranking and prompt refinement to 'feature/member1-rag-engine' (3 commits).
2026-08-29 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed parser optimizations and test dataset to 'feature/member2-doc-ingestion' (3 commits).
2026-08-29 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed analytics endpoints and database indexes to 'feature/member3-database-security' (3 commits).
2026-08-29 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed admin dashboard UI and custom window controls to 'feature/member4-ui-electron' (3 commits).
2026-08-29 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed evaluation service and golden dataset runner to 'feature/member5-analytics-evaluation' (3 commits).
2026-08-31 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Created 'develop' branch; orchestrated Pull Requests from all 5 feature branches and resolved merge conflicts.
2026-08-31 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Tested end-to-end document upload pipeline using 10 different Kaggle PDF documents via Electron UI.
2026-08-31 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Configured production-grade CORS configuration in Spring Security allowing electron:// and localhost origins.
2026-08-31 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Configured Electron IPC handlers for file opening, external link navigation, and system notifications.
2026-08-31 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Executed end-to-end test suite covering full user journey: Register -> Login -> Upload Doc -> Query -> View Citations.
2026-09-01 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Verified end-to-end RAG query flow from React chat input through Spring Boot to Neon pgvector and LLM.
2026-09-01 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Fixed bug where documents with special characters in filename failed during Neon metadata insertion.
2026-09-01 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Resolved JWT expiration handling: implemented refresh token rotation and 401 automatic redirect.
2026-09-01 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Packaged React frontend into production build; verified static asset serving inside Electron shell.
2026-09-01 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Identified and logged 6 integration defects in issue tracker; verified fixes across all team modules.
2026-09-02 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Conducted team code review session; standardized log formats, API error responses, and HTTP status codes.
2026-09-02 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Verified async processing notifications pop up correctly on desktop client upon indexing completion.
2026-09-02 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Verified Neon SSL connection resilience under transient cloud network reconnects.
2026-09-02 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Fixed chat auto-scroll glitch when streaming long multi-paragraph responses.
2026-09-02 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Conducted regression testing across all 15 functional requirements specified in SRS.
2026-09-03 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Profiled end-to-end query latency: average 850ms for first token arrival over local network.
2026-09-03 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Added automatic cleanup of temporary files in local server uploads directory.
2026-09-03 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Audited database connection leaks using HikariCP leakDetectionThreshold = 2000ms.
2026-09-03 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Added network connectivity banner that alerts user when Spring Boot backend is unreachable.
2026-09-03 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Measured overall test coverage: achieved 84.6% branch coverage across backend Java codebase.
2026-09-04 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Demonstrated integrated end-to-end system live to mentor Er. Ram Babu Buri during Saturday review.
2026-09-04 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Reviewed document upload stability and multi-file processing during mentor review.
2026-09-04 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented security and database stability validation to mentor during Saturday review.
2026-09-04 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated production Electron build installer to mentor during review.
2026-09-04 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented comprehensive test execution report to mentor during Saturday meeting.
2026-09-05 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed integration bugfixes to 'develop' branch (3 commits).
2026-09-05 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed file handling fixes to 'develop' branch (3 commits).
2026-09-05 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed CORS and JWT refresh enhancements to 'develop' branch (3 commits).
2026-09-05 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed desktop client integration fixes to 'develop' branch (3 commits).
2026-09-05 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed end-to-end test scripts and regression reports to 'develop' branch (3 commits).
2026-09-07 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Benchmarked Spring AI prompt throughput under concurrent load; optimized prompt string concatenation.
2026-09-07 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Benchmarked document parsing throughput under simultaneous multi-document uploads from Kaggle dataset.
2026-09-07 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Configured Neon PgBouncer connection pooler in transaction mode for high concurrency support.
2026-09-07 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Optimized React bundle size using Vite code-splitting and dynamic imports for Admin Dashboard and Settings.
2026-09-07 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Configured Apache JMeter test plan: 50 virtual users, 10-minute duration, ramp-up period 30 seconds.
2026-09-08 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Implemented parallel retrieval execution using Java CompletableFuture for hybrid search.
2026-09-08 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Optimized Apache PDFBox memory allocation using MemoryUsageSetting.setupTempFileOnly().
2026-09-08 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Tuned PostgreSQL configuration parameters: work_mem, maintenance_work_mem, and max_connections.
2026-09-08 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Reduced Electron application initial load time from 2.4s to 1.1s.
2026-09-08 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Recorded key metrics: 99th percentile latency = 1.4s, error rate = 0.0%, average throughput = 42 req/sec.
2026-09-09 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Reduced query embedding generation latency by 35% using local embedding cache.
2026-09-09 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Prevented OutOfMemoryError when parsing 100MB+ documents by streaming page extraction.
2026-09-09 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Analyzed slow query logs; optimized pgvector similarity search query execution plan.
2026-09-09 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Implemented virtualized list rendering in Document Manager to handle 500+ document chunks smoothly.
2026-09-09 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Tested system stability under memory stress (heap usage leveled off gracefully under garbage collection).
2026-09-10 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Hardened exception handlers with user-friendly error messages when upstream LLM rate limits hit.
2026-09-10 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Added queue limit for background indexing tasks (max 10 queued files, surplus queued with status WAITING).
2026-09-10 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Conducted database failover and auto-reconnect test during simulated network drops.
2026-09-10 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Eliminated unnecessary React re-renders in ChatMessageList using React.memo and useCallback hooks.
2026-09-10 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Generated load test performance summary report with charts and response time distributions.
2026-09-11 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Presented load testing results and latency improvements to mentor during Saturday review.
2026-09-11 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Reviewed ingestion scalability and memory profiling graphs with mentor.
2026-09-11 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Demonstrated database stress testing metrics to mentor Er. Ram Babu Buri.
2026-09-11 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated UI performance gains and low RAM footprint to mentor during review.
2026-09-11 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented JMeter performance report to mentor during Saturday review.
2026-09-12 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed performance optimizations to 'develop' branch (3 commits).
2026-09-12 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed ingestion memory optimizations to 'develop' branch (3 commits).
2026-09-12 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed database connection pooling tuning to 'develop' branch (3 commits).
2026-09-12 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed frontend performance optimizations to 'develop' branch (3 commits).
2026-09-12 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed JMeter test scripts and results to 'develop' branch (3 commits).
2026-09-14 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Authored Project Report Chapter 1: Introduction, Problem Statement, Objectives, and Scope of RAG.
2026-09-14 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Authored Project Report Chapter 3: Data Ingestion Architecture, Kaggle Dataset Extraction, and Chunking Algorithms.
2026-09-14 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Authored Project Report Chapter 2: Literature Review, Theoretical Background on Vector Databases & pgvector.
2026-09-14 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Captured high-resolution application screenshots of Electron UI (Chat, Document Manager, Citations, Admin).
2026-09-14 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Authored Project Report Chapter 7: Testing Methodologies, Evaluation Results, and Performance Benchmarks.
2026-09-15 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Authored Chapter 4: System Implementation details for Core RAG Engine, Prompt Engineering, and Spring AI.
2026-09-15 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Created high-resolution data flow diagrams illustrating recursive sliding-window chunking.
2026-09-15 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Authored Chapter 5: Database Schema Design, Neon Cloud Deployment, and Security Architecture.
2026-09-15 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Authored Project Report Chapter 6: User Interface Design, Electron Desktop Architecture, and User Experience.
2026-09-15 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Authored Chapter 8: Conclusion, Limitations, and Future Work (multi-modal RAG, graph-based RAG).
2026-09-16 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Drafted Research Paper Section III: System Architecture and RAG Orchestration Methodology.
2026-09-16 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Drafted Research Paper Section IV: Document Processing and Chunk Boundary Optimization.
2026-09-16 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Drafted Research Paper Section V: Vector Indexing Performance (HNSW vs IVFFlat) and Latency Analysis.
2026-09-16 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Designed UI walkthrough figures and state machine diagrams for inclusion in documentation.
2026-09-16 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Drafted Research Paper Section VI: Experimental Results, RAG Triad Evaluation, and Conclusion.
2026-09-17 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Verified code snippets, algorithmic pseudocode, and mathematical formulation of cosine similarity in paper.
2026-09-17 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Compiled table of supported MIME formats, parsing benchmarks, and tokenization accuracy.
2026-09-17 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Documented database backup protocols, encryption at rest, and JWT authentication flows.
2026-09-17 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Drafted user manual and quick-start guide for running the Electron desktop app.
2026-09-17 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Ran plagiarism check across all compiled chapters (achieved 8.4% plagiarism, well below 20% limit).
2026-09-18 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Reviewed Project Report Chapters 1 & 4 with mentor Er. Ram Babu Buri during Saturday review.
2026-09-18 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Presented Chapter 3 draft to mentor during Saturday review meeting.
2026-09-18 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented Chapters 2 & 5 and research paper data to mentor during Saturday review.
2026-09-18 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Presented UI chapters and user manual to mentor during Saturday review.
2026-09-18 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented testing chapter and plagiarism verification report to mentor during Saturday review.
2026-09-19 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Updated repository documentation and README.md with detailed setup and execution instructions (3 commits).
2026-09-19 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed documentation assets and diagrams to repository (3 commits).
2026-09-19 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed SQL schemas, migration scripts, and architecture docs to repository (3 commits).
2026-09-19 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed application screenshots and user guides to repository (3 commits).
2026-09-19 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Compiled all chapters into unified master Project Report document (3 commits).
2026-09-21 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Designed PPT Master Deck Slides 1-3 (Title, Problem Statement, System Architecture, RAG Pipeline).
2026-09-21 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Designed PPT Slide 4 (Document Ingestion Engine, Recursive Chunking & Apache Tika Pipeline).
2026-09-21 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Designed PPT Slide 5 (Neon Cloud Database, pgvector HNSW Indexing, Spring Security & JWT).
2026-09-21 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Designed PPT Slide 6 (React UI Design, Electron Desktop Integration & Streaming User Experience).
2026-09-21 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Designed PPT Slides 7-10 (Testing, JMeter Benchmarks, RAG Triad Evaluation Metrics & Future Roadmap).
2026-09-22 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Drafted 10-minute Demo Video script outlining speaking parts and feature demos for all 5 members.
2026-09-22 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Recorded screen capture segment demonstrating multi-format document upload from Kaggle and real-time chunking.
2026-09-22 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Recorded screen capture segment showing live Neon PostgreSQL console, pgvector queries, and JWT auth flow.
2026-09-22 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Recorded screen capture segment showing Electron desktop app, real-time token streaming, and source citation preview.
2026-09-22 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Recorded screen capture segment showing Admin Analytics Dashboard and automated Ragas evaluation runner.
2026-09-23 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Prepared Core RAG Engine viva voce answers (Spring AI, cosine distance math, context window budgeting).
2026-09-23 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Prepared viva voce answers on text parsing, tokenization algorithms, and handling unstructured data.
2026-09-23 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Prepared viva voce answers on vector indexing, cosine similarity vs Euclidean distance, and database scalability.
2026-09-23 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Prepared viva voce answers on Electron security model, IPC bridge, React state management, and SSE.
2026-09-23 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Prepared viva voce answers on RAG Triad (Context Precision, Faithfulness, Relevance) and testing methodologies.
2026-09-24 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Conducted mock viva with team members; reviewed potential cross-questioning from external examiner.
2026-09-24 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Participated in mock viva session; explained chunking overlap rationale.
2026-09-24 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Participated in mock viva; demonstrated live SQL queries in psql terminal.
2026-09-24 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Participated in mock viva; demonstrated Electron desktop app features.
2026-09-24 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Participated in mock viva; explained JMeter stress test graphs and error rates.
2026-09-25 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Presented PPT deck to mentor Er. Ram Babu Buri during Saturday review.
2026-09-25 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Reviewed ingestion demo clip and slides with mentor during Saturday review.
2026-09-25 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Reviewed database demo clip and slides with mentor during Saturday review.
2026-09-25 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Reviewed UI demo video clip with mentor during Saturday review.
2026-09-25 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Reviewed evaluation demo clip and final PPT deck with mentor Er. Ram Babu Buri.
2026-09-26 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Committed final PPT and video script to repository docs folder (3 commits).
2026-09-26 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed presentation slides and video assets to repository (3 commits).
2026-09-26 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed presentation slides and SQL demonstration scripts to repository (3 commits).
2026-09-26 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed presentation slides and UI demo assets to repository (3 commits).
2026-09-26 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed final compiled presentation slides and demo links to repository (3 commits).
2026-09-28 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Conducted final repository audit; verified all 5 member branches are merged cleanly into 'main'.
2026-09-28 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Verified all document parsing dependencies are shaded into the runnable Spring Boot JAR.
2026-09-28 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Verified Neon PostgreSQL database production schema, connection quotas, and automated cloud backups.
2026-09-28 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Built Electron Windows installer using electron-builder.
2026-09-28 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Conducted final regression testing on release v1.0.0 installer and backend JAR.
2026-09-29 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Created GitHub Release v1.0.0 with release notes, binary links, and documentation links.
2026-09-29 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Tested standalone file ingestion on clean Windows environment without development tools.
2026-09-29 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Exported final database schema DDL and sanitized sample vector data script for submission archive.
2026-09-29 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Tested installer execution on clean Windows 11 machine; verified desktop shortcut and uninstall routine.
2026-09-29 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Ran automated RAG Triad evaluation on production release: confirmed 92.4% aggregate faithfulness score.
2026-09-30 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Verified runnable Spring Boot executable JAR: 'java -jar rag-backend-1.0.0.jar' boots cleanly in 4.2 seconds.
2026-09-30 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Double-checked that no proprietary API keys or credentials exist in source code or sample files.
2026-09-30 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Configured environment variable documentation for database credentials and JWT secret keys.
2026-09-30 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Verified production build connects seamlessly to deployed backend and handles offline network states gracefully.
2026-09-30 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Compiled final testing verification certificate and code quality metric report.
2026-10-01 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Reviewed all repository branches to confirm minimum 3 commits/student per week requirement is satisfied.
2026-10-01 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Updated repository troubleshooting guide for PDF extraction on Windows paths.
2026-10-01 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Ran final database security and vulnerability scan (0 critical vulnerabilities found).
2026-10-01 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Created software user installation guide with step-by-step screenshots.
2026-10-01 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Organized submission archive containing Report, SRS, UML, PPT, Research Paper, and Video Link.
2026-10-02 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Presented packaged release v1.0.0 to mentor Er. Ram Babu Buri during Saturday review.
2026-10-02 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Presented standalone document ingestion test to mentor during Saturday review.
2026-10-02 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Presented database production readiness to mentor during Saturday review.
2026-10-02 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Demonstrated one-click installer to mentor Er. Ram Babu Buri during review.
2026-10-02 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Presented final testing certificate to mentor during Saturday review.
2026-10-03 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Pushed final signed release commit to 'main' branch (3 commits).
2026-10-03 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Committed documentation updates to 'main' branch (3 commits).
2026-10-03 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Committed sanitized database seed scripts to 'main' branch (3 commits).
2026-10-03 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Committed Electron build configuration and installer assets to 'main' branch (3 commits).
2026-10-03 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Committed final test verification summary to 'main' branch (3 commits).
2026-10-05 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Verified complete submission archive: Project Report PDF, SRS PDF, UML Diagrams, PPT, Research Paper, Video Link.
2026-10-05 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Verified and submitted all daily work log entries for Module 2 on the college portal.
2026-10-05 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Verified and submitted all daily work log entries for Module 3 on the college portal.
2026-10-05 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Verified and submitted all daily work log entries for Module 4 on the college portal.
2026-10-05 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Verified and submitted all daily work log entries for Module 5 on the college portal.
2026-10-06 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Compiled day-by-day work log for Team Leader and verified alignment with project milestones.
2026-10-06 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Prepared printed copy of Document Ingestion and Parsing documentation for viva panel.
2026-10-06 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Prepared printed copy of Database ER diagrams, pgvector schema, and security specifications.
2026-10-06 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Prepared printed copy of UI wireframes, Electron architecture diagrams, and user manual.
2026-10-06 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Prepared printed copy of Testing reports, JMeter performance graphs, and Research Paper.
2026-10-07 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Logged Week 14 final submission details on college Netlify portal under Team Leader account.
2026-10-07 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Verified all GitHub commits on 'feature/member2-doc-ingestion' and PR merge records.
2026-10-07 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Verified all GitHub commits on 'feature/member3-database-security' and PR merge records.
2026-10-07 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Verified all GitHub commits on 'feature/member4-ui-electron' and PR merge records.
2026-10-07 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Verified all GitHub commits on 'feature/member5-analytics-evaluation' and PR merge records.
2026-10-08 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 1.5 | Completed | Conducted final team briefing for external viva; rehearsed slide transitions and live demo sequence.
2026-10-08 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 1.5 | Completed | Reviewed viva questions on text chunking algorithms and edge-case handling.
2026-10-08 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 1.5 | Completed | Reviewed viva questions on vector search mathematics, indexing techniques, and JWT security.
2026-10-08 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 1.5 | Completed | Reviewed viva questions on Electron IPC security, React state management, and SSE streaming.
2026-10-08 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 1.5 | Completed | Reviewed viva questions on RAG Triad evaluation metrics, hallucination detection, and load testing.
2026-10-09 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2 | Completed | Attended final sign-off meeting with mentor Er. Ram Babu Buri; obtained mentor recommendation sign-off.
2026-10-09 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2 | Completed | Participated in final mentor sign-off review with mentor Er. Ram Babu Buri.
2026-10-09 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2 | Completed | Participated in final mentor sign-off review with mentor Er. Ram Babu Buri.
2026-10-09 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2 | Completed | Participated in final mentor sign-off review with mentor Er. Ram Babu Buri.
2026-10-09 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2 | Completed | Participated in final mentor sign-off review with mentor Er. Ram Babu Buri.
2026-10-10 | Shaurya Dixit | Module 1: Core RAG Engine & LLM Orchestration | 2.5 | Completed | Submitted final project repository URL and verified public accessibility for external evaluation.
2026-10-10 | Yashvardhan Singh Chauhan | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | 2.5 | Completed | Archived final module code and test logs in team submission drive.
2026-10-10 | Vaibhav Tank | Module 3: Neon PostgreSQL Vector Store & Spring Security | 2.5 | Completed | Archived database DDL scripts and connection configuration guides.
2026-10-10 | Rajveer Singh Ranawat | Module 4: React TypeScript UI & Electron Desktop Integration | 2.5 | Completed | Archived Electron installer build and frontend source assets.
2026-10-10 | Yashpal Singh Bhati | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | 2.5 | Completed | Completed master compilation of all submission artifacts and portal submission verifications.

## Weekly Project Reports
Week | Date Range | Submitted By | GitHub / Report Link | Work Completed This Week | Problems Faced | Plan for Next Week
Week 1 | 2026-07-06 to 2026-07-11 | Shaurya Dixit | https://github.com/shauryadixit/docuquery-rag/tree/main | Formed 5-member team with guide Er. Ram Babu Buri. Finalized topic: 'DocuQuery AI: Enterprise RAG using Spring Boot, Neon pgvector, Electron, and Kaggle Research Corpus'. Partitioned into 5 distinct modules. Prepared project abstract. | Evaluating Kaggle multi-domain research paper dataset vs arXiv corpus for token size and formatting compatibility. | Formulate IEEE 830 Software Requirements Specification (SRS) for all 5 modules.
Week 2 | 2026-07-13 to 2026-07-18 | Vaibhav Tank | https://github.com/shauryadixit/docuquery-rag/tree/main | Compiled complete IEEE 830 SRS document. Defined functional requirements FR1-FR15 (Kaggle dataset upload, chunking, pgvector search, JWT, SSE streaming) and non-functional requirements (latency, security, memory). | Defining latency constraints for 1536-dim vector searches over cloud Neon DB under 100ms. | Design UML diagrams (Use Case, Class, Sequence, Component, ER) for all modules.
Week 3 | 2026-07-20 to 2026-07-25 | Shaurya Dixit | https://github.com/shauryadixit/docuquery-rag/tree/main | Designed complete UML models: System Use Case Diagram, Class Diagram for Spring Boot entities and services, Sequence Diagrams for RAG Query and Kaggle Ingestion, Activity Diagram for chunking, and Component/ER models. | Modeling asynchronous streaming response between Spring Boot WebFlux and Electron IPC renderer. | Execute database DDL migrations on Neon PostgreSQL, setup HNSW index, initialize React+Vite project.
Week 4 | 2026-07-27 to 2026-08-01 | Rajveer Singh Ranawat | https://github.com/shauryadixit/docuquery-rag/tree/main | Configured Neon PostgreSQL cloud database, executed DDL migration scripts with HNSW index. Initialized React 18 + TypeScript + Vite frontend with Electron desktop shell. Downloaded Kaggle academic test corpus. | Tuning HNSW vector index parameters (m=16, ef_construction=64) on Neon for optimal lookup speed. | Begin Module Coding Phase 1: Initialize Spring Boot project, configure build dependencies, push initial commits.
Week 5 | 2026-08-03 to 2026-08-08 | Shaurya Dixit | https://github.com/shauryadixit/docuquery-rag/tree/main | Implemented core RAG prompt formatting and query processing pipeline. Completed document parsing and recursive sliding-window chunking in Java. Implemented Spring Security JWT authentication and role-based filters. Built React chat message component. | Handling UTF-8 character encoding and ligatures in scanned PDF documents from Kaggle. | Implement vector embedding generation, store chunks in Neon pgvector, connect Electron frontend to Spring Boot.
Week 6 | 2026-08-10 to 2026-08-15 | Yashvardhan Singh Chauhan | https://github.com/shauryadixit/docuquery-rag/tree/main | Connected Kaggle document chunking pipeline to embedding generation service. Implemented batch insertion into Neon PostgreSQL using pgvector JDBC prepared statements. Built multipart file upload controller in Spring Boot and drag-and-drop file uploader in React. | Batch inserting large vectors caused memory spikes; resolved by implementing batched paging of 50 chunks. | Implement Server-Sent Events (SSE) streaming chat API and connect Electron frontend to streaming endpoint.
Week 7 | 2026-08-17 to 2026-08-22 | Vaibhav Tank | https://github.com/shauryadixit/docuquery-rag/tree/main | Implemented Server-Sent Events (SSE) streaming API (/api/rag/chat/stream) delivering token-by-token LLM responses. Implemented dynamic source citation referencing linking generated statements to exact Kaggle paper excerpts. Integrated desktop native notifications in Electron. | Handling client disconnection mid-stream and ensuring LLM stream cancels promptly to conserve compute tokens. | Implement RAG Triad evaluation metrics (Faithfulness, Relevance, Groundedness) and build Admin Analytics dashboard.
Week 8 | 2026-08-24 to 2026-08-29 | Yashpal Singh Bhati | https://github.com/shauryadixit/docuquery-rag/tree/main | Built automated RAG Triad evaluation service measuring Context Relevance, Faithfulness, and Answer Relevance against Kaggle ground-truth questions. Created Admin Analytics Dashboard in React displaying real-time query latency and token usage graphs. | Formulating a cost-effective evaluation metric that calculates faithfulness without incurring high extra LLM API latency. | Perform system-wide integration, end-to-end testing between Electron desktop application, Spring Boot, and Neon PostgreSQL.
Week 9 | 2026-08-31 to 2026-09-05 | Shaurya Dixit | https://github.com/shauryadixit/docuquery-rag/tree/main | Merged 5 feature branches into 'develop' integration branch. Conducted end-to-end data flow testing from Electron Desktop App -> Spring Boot Backend -> Neon Cloud PostgreSQL -> Vector Search -> Streaming Response. Resolved CORS, token expiration, and payload size issues. | Electron client encountered CORS errors when sending preflight OPTIONS requests to Spring Boot; resolved by configuring explicit CorsConfigurationSource in SecurityFilterChain. | Execute load testing, stress testing, edge-case validation, and security penetration review.
Week 10 | 2026-09-07 to 2026-09-12 | Vaibhav Tank | https://github.com/shauryadixit/docuquery-rag/tree/main | Conducted load testing using Apache JMeter simulating 50 concurrent users querying the RAG system. Optimized Neon pgvector HNSW query performance, tuned HikariCP connection pool, reduced React bundle size, and verified memory stability. | Under 50 concurrent users, Neon PostgreSQL connection pool was exhausted; resolved by configuring PgBouncer connection pooling and tuning Spring Boot max-pool-size. | Prepare Project Report draft, generate UML diagrams for final submission, draft Research Paper on RAG optimization.
Week 11 | 2026-09-14 to 2026-09-19 | Yashvardhan Singh Chauhan | https://github.com/shauryadixit/docuquery-rag/tree/main | Compiled comprehensive Project Report following Arya College formatting guidelines. Drafted IEEE format Research Paper titled 'Optimizing Enterprise Retrieval-Augmented Generation using Hybrid Search and pgvector in Cloud-Native Architecture'. Generated finalized UML diagrams and architectural blueprints. | Ensuring college plagiarism limit (<20%) is strictly respected across all chapters of the project report and research paper draft. | Design PowerPoint presentation (PPT) master slides, record comprehensive application demo video, prepare viva voce answers.
Week 12 | 2026-09-21 to 2026-09-26 | Shaurya Dixit | https://github.com/shauryadixit/docuquery-rag/tree/main | Created 10-slide PowerPoint (PPT) presentation deck. Recorded 10-minute HD demo video showcasing live system architecture, Kaggle document upload, pgvector similarity search, token-by-token streaming, source citations, and admin analytics. Conducted mock viva voce sessions. | Recording demo video with clean audio and demonstrating both local Electron desktop window and Neon cloud database queries simultaneously. | Final branch merge into 'main', tag release v1.0.0, print project reports, submit all deliverables to college portal.
Week 13 | 2026-09-28 to 2026-10-03 | Yashpal Singh Bhati | https://github.com/shauryadixit/docuquery-rag/tree/main | Completed final code freeze, merged all tested branches into 'main', tagged GitHub release v1.0.0. Packaged runnable Electron installer (.exe) and runnable Spring Boot JAR. Verified cross-platform execution on clean test machine. | Packaging Electron installer with bundled backend URL configuration without exposing cloud database credentials. | Submit all final documents, project report, research paper, PPT, video link, and daily/weekly logs to college portal.
Week 14 | 2026-10-05 to 2026-10-10 | Shaurya Dixit | https://github.com/shauryadixit/docuquery-rag/tree/main | Completed all final submissions on college portal (javapbl5thsem.netlify.app). Uploaded Project Report, SRS, PPT, Research Paper, GitHub repo link, and Demo video URL. Completed all daily work logs and weekly report submissions for all 5 team members. Ready for Final External Viva. | Ensuring portal daily work logs and weekly summaries align perfectly with commit timestamps and deliverables. | Attend Final PBL External Viva Examination, deliver stellar project demonstration, and secure maximum marks.

## Team & 5-Module Mapping
Member Name | Project Role | Assigned Module | Git Branch | Core Technologies | Key Deliverables
Shaurya Dixit | Team Leader & Core RAG Architect | Module 1: Core RAG Engine & LLM Orchestration | feature/member1-rag-engine | Java 21, Spring Boot 3, Spring AI, WebFlux, Caffeine Cache | RAG retrieval controller, prompt engineering, token streaming SSE, hallucination guardrails
Yashvardhan Singh Chauhan | Data Engineer & Kaggle Ingestion Lead | Module 2: Document Ingestion, Parsing & Chunking (Kaggle Dataset) | feature/member2-doc-ingestion | Apache Tika, Apache PDFBox 3, JTokkit, Spring Async | Kaggle research paper parser (PDF, DOCX, TXT), recursive sliding chunker, multipart upload worker
Vaibhav Tank | Database Architect & Security Engineer | Module 3: Neon PostgreSQL Vector Store & Spring Security | feature/member3-database-security | Neon PostgreSQL, pgvector (HNSW), Spring Security 6, JWT, Bucket4j | Cloud Neon DB schema, HNSW vector cosine search, JWT RBAC security, rate-limiting, audit logging
Rajveer Singh Ranawat | Frontend & Desktop Architecture Lead | Module 4: React TypeScript UI & Electron Desktop Integration | feature/member4-ui-electron | Electron 30, React 18, TypeScript, Tailwind CSS, Vite, Axios | Cross-platform desktop app, real-time chat streaming UI, citation viewer, document drag-and-drop
Yashpal Singh Bhati | QA, RAG Evaluation & Analytics Lead | Module 5: RAG Triad Evaluation, Performance Analytics & Testing | feature/member5-analytics-evaluation | JUnit 5, Mockito, Apache JMeter, Recharts, JaCoCo | RAG Triad evaluation metrics (Faithfulness/Relevance on Kaggle dataset), JMeter load tests, Admin telemetry dashboard